## Sheet1
Solar Energy System
ACTIVITY | PLAN START | PLAN DURATION | PERIODS (months)
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
General Plan | 1 | 2 | bar: PERIODS (months) 1 to PERIODS (months) 2
Schedule | 1 | 2 | bar: PERIODS (months) 1 to PERIODS (months) 2
SDLC | 1 | 2 | bar: PERIODS (months) 1 to PERIODS (months) 2
User Case | 2 | 2 | bar: PERIODS (months) 2 to PERIODS (months) 3
Cost plan | 2 | 2 | bar: PERIODS (months) 2 to PERIODS (months) 3
Design safe | 3 | 2 | bar: PERIODS (months) 3 to PERIODS (months) 4
Disgn security | 3 | 3 | bar: PERIODS (months) 3 to PERIODS (months) 5
Develop carefully | 3 | 3 | bar: PERIODS (months) 3 to PERIODS (months) 5
Develop quality | 3 | 3 | bar: PERIODS (months) 3 to PERIODS (months) 5
Testing | 6 | 1 | bar: PERIODS (months) 6